## WBS
Lopes Manufacturing Infrastructure Final Proposal
The development of a main and secondary sites
Work Breakdown Structure
ID | Task | SubTask | Estimated Time (Hours)
1.1 | LAN Switches |  | a | m | b | (a+4m+b)/6
1.1.1 |  | Place them in the Rack | 0.75 | 1.15 | 1.75 | 1.1833
1.1.2 |  | Plug Cables in the Back and Organize Them | 0.5 | 1 | 1.5 | 1
1.1.3 |  | Configure Layer 2 Switch | 1 | 1.5 | 1.75 | 1.4583
1.1.4 |  | Configure Layer 3 Switch | 0.3 | 0.6 | 1 | 0.61667
1.1.5 |  | Test all connections and verify everything works | 0.15 | 0.5 | 0.85 | 0.5
1.2 | Firewalls
1.2.1 |  | Place them in the Rack | 0.5 | 0.75 | 1 | 0.75
1.2.2 |  | Plug Cables in the Back and Organize Them | 0.5 | 1 | 1.5 | 1
1.2.3 |  | Configure the Firewall | 2 | 3.5 | 4.5 | 3.4167
1.2.4 |  | Configure ISP Connection | 3 | 4 | 5.5 | 4.0833
1.2.5 |  | Apply VPN | 1 | 2 | 3 | 2
1.2.6 |  | Test Connection | 0.5 | 1.5 | 2 | 1.4167
1.3 | DMZ Servers
1.3.1 |  | Place them in the Rack | 0.25 | 0.5 | 1 | 0.53
1.3.2 |  | Configure The Servers | 1 | 2 | 3.5 | 2.09
1.3.3 |  | Test the Connection | 2 | 4 | 8 | 4.3333
1.4 | ISP Modems
1.4.1 |  | Configure Modem/Create Necesarry Ips | 3 | 5.5 | 8 | 5.5
1.5 | Test
1.5.1 |  | Test all connections and verify everything works | 1 | 1.75 | 2.5 | 1.75
|  |  | Total |  |  | 31.6283
Estimated Times Explanation
a -> Optimistic time: the minimum reasonable period of time in which the activity can be completed. Should be a < 1% chance of completing it in less time.
m -> Most likely time: the best guess of the time required.
b -> Pessimistic time: the maximum reasonable period of time in which the activity can be completed. Should be a < 1% chance of completing it in more time.
INSTRUCTIONS FOR USING THIS WORKSHEET
1. Change the "project title".
2. Add additional descriptive information about the project.
3. Modify the major tasks to match major tasks in your project. You may not have five major tasks (you could have less or more). Update the names to match your project.
4. Modify the subtasks of each major task to match your project (insert/delete rows as needed). Update the names to match your project.
5. For each subtask, update the a, m, and b values for time. Do not change the formula in the far right column.
Remember, this is a template to get you started. You're not filling this out as is. No two projects are exactly alike.